## Project Planner
LEAD Trivia App
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Design Initial Competition Screen - Show Teams | 1 | 1 |  |  | 0%
Implement User Screen - View Lobby | 1 | 1 | 1 |  | 0%
Implement User Screen - View Team | 1 | 1 | 1 |  | 0%
Implement User Control - Create Team | 1 | 7 |  |  | 0%
Implement User Control - Join Team | 1 | 7 |  |  | 0%
Implement User Control - Assign Random Name | 1 | 7 |  |  | 0%
Implement User Control - Leave Team | 1 | 7 |  |  | 0%
Implement User Control - Change Team | 1 | 7 |  |  | 0%
Implement User Control - Change Team Name | 1 | 7 |  |  | 0%
Implement User Screen - Question Display - Multiple Choice | 7 | 7 |  |  | 0%
Implement User Screen - Question Display - Fill in the Blank | 7 | 7 |  |  | 0%
Implement User Screen - Question Display - AV Question | 7 | 7 |  |  | 0%
Implement User Screen - Answer Display | 7 | 7 |  |  | 0%
Implement Game Question Timeout | 7 | 7 |  |  | 0%
Implement User Screen - Round Result | 13 | 7 |  |  | 0%
Implement User Screen - Final Results | 13 | 7 |  |  | 0%
Implement User Control - Submit Answer to Multiple Choice | 13 | 7 |  |  | 0%
Implement User Control - Submit Answer to Fill in the Blank | 13 | 7 |  |  | 0%
Implement Game Team Answer Selection | 13 | 7 |  |  | 0%
Implement User Selected Answer Feedback | 13 | 7 |  |  | 0%
Implement Admin Login | 27 | 7 |  |  | 0%
Implement Admin Settings | 27 | 7 |  |  | 0%
Implement Admin Create Game Option | 27 | 7 |  |  | 0%
Implement Admin Game Start/Finished Setting | 27 | 7 |  |  | 0%
Implement Admin Edit Game Option | 33 | 7 |  |  | 0%
Implement Admin Upload Game Assets | 33 | 7 |  |  | 0%
Implement Competition Screen - View Lobby | 39 | 7 |  |  | 0%
Implement Competition Screen - Question Display | 39 | 7 |  |  | 0%
Implement Competition Screen - Answer Display | 39 | 7 |  |  | 0%
Implement Competition Screen - Round Results | 39 | 7 |  |  | 0%
Implement Competition Screen - Final Results | 39 | 7 |  |  | 0%