## Sheet1
Task | Start | Finish | Duration | Priority
Design Initial Competition Screen - Show Teams | 2020-02-20 | 2020-02-21 | 1 | 4
Implement User Screen - View Lobby | 2020-02-20 | 2020-02-21 | 1 | 1
Implement User Screen - View Team | 2020-02-20 | 2020-02-21 | 1 | 2
Implement User Control - Create Team | 2020-02-20 | 2020-02-27 | 7 | 1
Implement User Control - Join Team | 2020-02-20 | 2020-02-27 | 7 | 1
Implement User Control - Assign Random Name | 2020-02-20 | 2020-02-27 | 7 | 4
Implement User Control - Leave Team | 2020-02-20 | 2020-02-27 | 7 | 3
Implement User Control - Change Team | 2020-02-20 | 2020-02-27 | 7 | 3
Implement User Control - Change Team Name | 2020-02-20 | 2020-02-27 | 7 | 4
Implement User Screen - Question Display - Multiple Choice | 2020-02-27 | 2020-03-05 | 7 | 1
Implement User Screen - Question Display - Fill in the Blank | 2020-02-27 | 2020-03-05 | 7 | 1
Implement User Screen - Question Display - AV Question | 2020-02-27 | 2020-03-05 | 7 | 1
Implement User Screen - Answer Display | 2020-02-27 | 2020-03-05 | 7 | 1
Implement Game Question Timeout | 2020-02-27 | 2020-03-05 | 7 | 4
Implement User Screen - Round Result | 2020-03-05 | 2020-03-12 | 7 | 3
Implement User Screen - Final Results | 2020-03-05 | 2020-03-12 | 7 | 3
Implement User Control - Submit Answer to Multiple Choice | 2020-03-05 | 2020-03-12 | 7 | 1
Implement User Control - Submit Answer to Fill in the Blank | 2020-03-05 | 2020-03-12 | 7 | 1
Implement Game Team Answer Selection | 2020-03-05 | 2020-03-12 | 7 | 2
Implement User Selected Answer Feedback | 2020-03-05 | 2020-03-12 | 7 | 2
Implement Admin Login | 2020-03-26 | 2020-04-02 | 7 | 3
Implement Admin Settings | 2020-03-26 | 2020-04-02 | 7 | 3
Implement Admin Create Game Option | 2020-03-26 | 2020-04-02 | 7 | 1
Implement Admin Game Start/Finished Setting | 2020-03-26 | 2020-04-02 | 7 | 1
Implement Admin Edit Game Option | 2020-04-02 | 2020-04-09 | 7 | 1
Implement Admin Upload Game Assets | 2020-04-02 | 2020-04-09 | 7 | 2
Implement Competition Screen - View Lobby | 2020-04-09 | 2020-04-16 | 7 | 2
Implement Competition Screen - Question Display | 2020-04-09 | 2020-04-16 | 7 | 2
Implement Competition Screen - Answer Display | 2020-04-09 | 2020-04-16 | 7 | 2
Implement Competition Screen - Round Results | 2020-04-09 | 2020-04-16 | 7 | 2
Implement Competition Screen - Final Results | 2020-04-09 | 2020-04-16 | 7 | 2